## Overview
Starting Date | Link | Total Defects | Reviewed Defects | Today's Bug Count
PC | Resource 1 | 5 | 0 | 0
iPad | Resource 2 | 125 | 5 | 0
| Total | 125 | 5 | 0

## PC
|  |  | Overall | Today
|  | A | 0 | 0
|  | B | 0 | 0
|  | C | 0 | 0
|  | S | 0 | 0
|  | Trivial | 0 | 0
|  | Total | 0 | 0
Date | Defect ID | Summary | Actual Result | Steps to Reproduce | Description | Configuration | Severity | To Log | Comments

## iPad
|  |  |  | Overall | Today
|  |  | A | 18 | 0
|  |  | B | 47 | 0
|  |  | C | 53 | 0
|  |  | S | 0 | 0
|  |  | Trivial | 0 | 0
|  |  | Total | 118 | 0
Date | Defcet ID | Summary | Description | Steps to Reproduce | Device Name | Actual | Severity | To Log | Comments
2014-08-28 | 67379 | 505' company Logo does not appear after launching the game. | Tested on Build: v 0.09 | 1. Install and launch Ember RPG. Repro rate: 5/5 | 505' company Logo does not appear after launching the game. | 505'Company logo should be present after launching the game. | A
2014-08-28 | 67383 | The game does displays load game options after launching the game. | Tested on Build: v 0.09 | Steps To Reproduce: 1. Install and launch Ember RPG. 2. Rescue Kwan. 3. Save the game. 4. Quit and relaunch the game. Actual Result: The game does displays load game options after launching the game. Expected Result: The game should displays Load game option after launching the game. Repro rate: 5/5 | The game does displays load game options after launching the game. | The game should displays Load game option after launching the game. | B
2014-08-28 | 67413 | Framerate drop is observed while moving the character in the free world. | Tested on Build: v 0.09 | Steps to Reproduce: 1. Launch and Launch Ember RPG. 2. Move the character in the free world. Actual Result: Framerate drop is observed. Expected Result: The game should function and proceed normally without any lag. Repro rate: 5/5 | Framerate drop is observed | The game should function and proceed normally without any lag. | B
2014-08-28 | 67415 | Light bringer head disappears after removing the Ancient Rags from the Light bringer's Inventory tab. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Select Light bringer inventory tab. 3. Drag Ancient Rags out of the Light bringer's Inventory tab. 4. Close the Inventory tab and observe Light bringer. Actual Result: 'Light bringer head disappears. Expected Result: 'Light bringer head should be displayed after removing Ancient Rags from the Inventory tab. Repro rate: 5/5 | Light bringer head disappears. | Light bringer head should be displayed after removing Ancient Rags from the Inventory tab. | B
2014-08-28 | 67417 | Navigation arrow is not displayed while progressing throughout the game. | Tested on Build: v 0.09 | Steps to Reproduce: 1. Launch Ember RPG. 2. Start Progressing in the game. Actual Result: Navigation arrow is not displayed. Expected Result: Navigation arrow should be displayed throughout the game. Repro rate: 5/5 | Navigation arrow is not displayed. | Navigation arrow should be displayed throughout the game. | B
2014-08-28 | 67420 | Tutorial mode is not displayed after launching the game with a fresh start. | Tested on Build: v 0.09 | 1. Launch Ember RPG. Actual Result: Tutorial mode is not displayed. Expected Result: Tutorial mode should be displayed. Repro rate: 5/5 | Tutorial mode is not displayed. | Tutorial mode should be displayed. | B
2014-08-28 | 67421 | Audio options are not displayed under the Setting menu. | Note: SFX and Music options are missing. Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Select Settings from the Main Menu. Actual Result: Audio options are not displayed. Expected Result: Audio options should be displayed. Repro rate: 5/5 | Audio options are not displayed. | Audio options should be displayed. | B
2014-08-28 | 67428 | Camera angle moves after opening inventory tab. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Tap on Inventory tab under Main menu. Notice the camera angle Actual Result: Camera angle moves after opening inventory tab. Expected Result: Camera angle should remain same after opening inventory tab. Repro rate: 5/5 | Camera angle moves after opening inventory tab. | Camera angle should remain same after opening inventory tab. | C
2014-08-28 | 67425 | The game crashes after loading the previously saved game five to six times. | Tested on Build: v 0.09 | Steps to Reproduce: 1. Install and launch Ember RPG. 2. Rescue Kwan. 3. Save the game. 4. Move in the world anywhere. 5. Load the saved game. 6. Repeat step no 4 and 5 atleast five to six time. Actual Result: The game crashes after loading the previously saved game five to six times. Repro rate: 3/10 | The game crashes after loading the previously saved game five to six times. | .. | A
2014-08-28 | 67431 | The game does not displays quit confirmation message while quitting the game. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Open settings menu. 3. Tap on Quit option. Actual Result: The game does not display quit confirmation message while quitting the game. Expected Result: The game should display quit confirmation message. Repro rate: 5/5 | The game does not display quit confirmation message while quitting the game. | The game should display quit confirmation message. | B
2014-08-28 | 67433 | The game resumes from the pause if the player hides the Main menu after pausing the game. | Tested on Build: v 0.09 | Steps to Reproduce: 1. Launch Ember RPG. 2. Pause the game. 3. Hide the Main menu. Actual Result: The game resumes from the pause if the player hides the Main menu after pausing the game. Expected Result: The game should resume only after tapping on Play button the game. Repro rate: 5/5 | The game resumes from the pause if the player hides the Main menu after pausing the game. | The game should resume only after tapping on Play button the game. | B
2014-08-29 | 67445 | The game crashes randomly after moving in the world and then tapping on any Main Menu option. | Tested on Build: v 0.09 | Steps To Reproduce: 1. Launch Ember RPG. 2. Move around the world. 3. Tap on any Main Menu option. 4. Repeat step no 2 and 3 atleast Eight to Ten times. Actual Result: The game crashes randomly after moving in the world and then tapping on any Main Menu option. Repro rate: 3/10 | The game crashes randomly after moving in the world and then tapping on any Main Menu option. | .. | A
2014-08-29 | 67447 | Dialogs and Audio does not match when Lightbringer interacts with Kwan. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Interact with Kwan. 3. Select option 'What happened to me? Are you hurt?' and listen to the audio. Actual Result: Dialogs and Audio does not match when Lightbringer interacts with Kwan. Expected Result: The Dialogs and Audio should match. Repro rate: 5/5 | Dialogs and Audio does not match when Lightbringer interacts with Kwan. | The Dialogs and Audio should match. | C
2014-08-29 | 67450 | The game crashes after using Fast Travel option to move around the map. | Tested on Build: v 0.09 | Steps To Reproduce: 1. Launch Ember RPG. 2. Open Map from Main menu. 3. Tap on Fast Travel. 4. Select location Ember Mines. Actual Result: The game crashes after using Fast Travel option to move around the map. Repro rate: 3/5 | The game crashes after using Fast Travel option to move around the map. | .. | A
2014-08-29 | 67459 | The game crashes after keeping the device idle for Five minutes and then moving anywhere in the world. | Tested on Build: v 0.09 Note: Due to Low Repro rate we were unable to capture logs for this bug. | Steps To Reproduce: 1. Launch Ember RPG. 2. Keep the device idle for Five minutes. 3. Move anywhere in the world. Actual Result: The game crashes after keeping the device idle for Five minutes and then moving anywhere in the world. Repro rate: 2/10 | The game crashes after keeping the device idle for Five minutes and then moving anywhere in the world. | .. | A
2014-08-29 | 67454 | The game crashes after entering in cave entrance door in first chapter. | Tested on Build: v 0.09 | Steps To Reproduce: 1. Launch Ember RPG. 2. Move towards the first cave door. 3. Enter in cave entrance door. Actual Result: The game crashes after entering in cave entrance door in first chapter. Repro rate: 4/10 | The game crashes after entering in cave entrance door in first chapter. | .. | A
2014-08-29 | 67456 | The game opens statistics menu during the battle when player accidently taps on character Kwan. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Enter in first battle and then tap on character Kwan. Actual Result: The game opens statistics menu during the battle when player accidently taps on character Kwan. Expected Result: The game should not open statistics menu during the battle after tapping character Kwan. Repro rate: 5/5 | The game opens statistics menu during the battle when player accidently taps on character Kwan. | The game should not open statistics menu during the battle after tapping character Kwan. | B
2014-08-29 | 67457 | Multiple empty slot windows can be opened after tapping on the dead enemies. | Tested on Build: v 0.09 | 1. Install and launch Ember RPG. 2. Rescue Kwan. 3. Proceed with the gameplay and defeat 3 thieves. 4. Collect all items from the dead enemies. 5. Click on the dead thieves multiple times. Observe multiple Empty slot popups on the screen. Actual Result: Multiple empty slot window popups are displayed on the screen. Expected Result: The user should not able to tap on dead enemies after collecting all items from them. Repro rate: 5/5 | Multiple empty slot window popups are displayed on the screen. | The user should not able to tap on dead enemies after collecting all items from them. | B
2014-08-29 | 67458 | The player is not able to unequip items from the Item slot. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Proceed with the game play and collect Health Potion. 4. Go to Inventory > Tap on Potions menu. 5. Drag and drop Health Potion into Item Slot in the HUD. 6. Try to Drag and drop Health Potion from Item Slot to Inventory. Actual Result: The player is not able to Drag and drop Health Potion from Item Slot to Inventory. Expected Result: The player should be able to unequip Heal potions from the Item Slot. | The player is not able to Drag and drop Health Potion from Item Slot to Inventory. | The player should be able to unequip Heal potions from the Item Slot. | B
2014-09-01 | #67503 | Inventory items can be placed in the air. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Move to the Stone Door. 3. Remove Ancient Rags and Time Clubber and place them on the door. 4. Zoom in with two finger gesture. Actual Result: Items can be placed in the air. Expected Result: The player should not be able to place items in the air. Repro rate: 5/5 |  |  | B
2014-09-01 | 67505 | Ancient Rags is not displayed in the player's inventory menu after opening for the first time. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Move to the Stone Door. 4 Tap on inventory menu. 3. Tap on the player's inventory tab. Actual Result: Ancient Rags is not displayed for the first time. Expected Result: Ancient Rags should be displayed always after opening player's inventory menu. Repro rate: 3/5 |  |  | B
2014-09-01 | 67507 | Mini map is not displayed while completing the Quest. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Look for the Mini map on the in-game screen. Actual Result: Mini map is not displayed on the screen. Expected Result: Mini map should be displayed at the top right corner of the screen. Repro rate: 5/5 |  |  | C
2014-09-01 | 67509 | Camera angle is not focused properly on the character while moving from one place to another. | Tested on Build: v 0.09 | Steps to Reproduce: 1. Launch Ember RPG. 2. Move the character on the map. Notice the camera angle. Actual Result: Camera angle is not focused properly on the character. Expected Result: Character is not center alligned properly while moving. Repro rate: 5/5 |  |  | C
2014-09-01 | 67510 | Delete option is not provided under Save slot tab. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Tap on the Settings menu. 3. Tap on Save Option > Slot option . Actual Result: Delete option is not provided. Expected Result: Delete option should be provided, as it helps the user to save new game state. Repro rate: 5/5 |  |  | B
2014-09-01 | 67513 | Crash occurs randomly after tapping on multiple tabs under the settings menu. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Tap on the Settings menu. 3. Tap on multiple option simultaneously. Actual Result: Crash occurs. Repro rate: 3/5 |  |  | A
2014-09-02 | 67680 | Characters climb on arc like structure after moving near the arc near the first cave. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Move towards the first cave door. 3. Move near the arc like structure just left to cave door. Actual Result: Characters climb on arc like structure after moving near the arc near the first cave. Expected Result: Character should move under the arc like arc like structure. Tested on build: v 0.09 Repro rate: 5/5 |  |  | C
2014-09-02 | 67682 | Dialogs and Audio does not match when Lightbringer interacts with Stephan. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Move and enter in first cave door. 3. Interact with Stephan. 4. Select option what Job are you Doing? and listen to the audio. Actual Result: Dialogs and Audio does not match when Lightbringer interacts with Stephan. Expected Result: The Dialogs and Audio should match. Tested on build: v 0.09 Repro rate: 5/5 |  |  | C
2014-09-02 | 67683 | The game displays warning 'Can't find animation…Player (5001349554 -1)' after loading the saved game. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Move and enter in first cave door. 3. Save and quit the game. 4. Load same gamestate. Actual Result: The game displays warning 'Can't find animation…Player (5001349554 -1)' after loading the saved game. Expected Result: The game should not display warning after loading the saved game. Tested on build: v 0.09 Repro rate: 5/5 |  |  | B
2014-09-02 | 67684 | Click & drag navigation pointer remains on the screen when user moves and releases the pointer on LightBringer HUD icon. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Open Lightbringers stats menu from top left corner of the screen. 3. Drag and release the navigation pointer on stats menu. 4. Close the stats menu. Actual Result: Click & drag navigation pointer remains on the screen when user moves and releases the pointer on LightBringer HUD icon. Expected Result: The game should not open stats menu after releasing the pointer on LightBringer HUD icon. Tested on build: v 0.09 Repro rate: 5/5 |  |  | C
2014-09-02 | 67685 | The player is able to select empty load slot. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Open Settings menu > Load. 3. Tap on empty slot. Actual Result: The player is able to select empty load slot. Expected Result: The user should not be able to select empty slot while loading a game. Tested on build: v 0.09 Repro rate: 5/5 |  |  | C
2014-09-02 | 67692 | The user has to tap twice on the same item before picking it up. | Tested on Build: v 0.09 | Steps to Reproduce: 1. Launch Ember RPG. 2. Open Inventory menu. 3. Select time clubber from inventory tab and Drag it in character inventory tab. 4. Drop Time Clubber from the character inventory tab 5. Move away from the weapon and again go near and pick it up. 6. Notice player has to tap twice for picking up the weapon. Actual Result: The user has to tap twice. Expected Result: The user should be able to collect any item by taping once. iPad 2 (7.0) |  |  | C
2014-09-02 | 67695 | The text "Merchants" overlaps on the "Lightbringer" after clicking on Luther the Merchant in Deep Barrows. | Tested on Build: v 0.09 | Steps to Reproduce: 1. Launch the RPG. 2. Select map. 3. Click on Fast Travel. 4. Click on Deep Barrows. 5. Click on Merchant. 6. Notice Title text. Actual Result: The text Merchants overlaps on the Lightbringer. Expected Result: The text Merchants and Light Bringer should be properly aligned. iPad 2 (7.0) |  |  | C
2014-09-02 | 67699 | The player is able to purchase any weapon at 0 Coins from the Luther the Merchant in Deep Barrows. | Tested on Build: v 0.09 | Steps to Reproduce: 1. Launch the RPG. 2. Select map. 3. Click on Fast Travel. 4. Click on Deep Barrows. 5. Click on Merchant. 6. Select Weapons. 7. Buy any weapon. Actual Result: The player is able to purchase any weapon at 0 Coins. Expected Result: Appropriate number of coins should be required for purchasing any weapon. iPad 2 (7.0) |  |  | B
2014-09-02 | 67703 | Random Crash occurs after removing Ancient Rags from player's inventory and dragging it into main inventory tab. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Move Lightbringer near to the locked Stone Door. 3. Open Character's inventory window. 4. Open Inventory window. 5. Drag Ancient Rags from Character's window and drop it into inventory window and tap rapidly on it. 6. Repeat 4 and 5 step. Actual Result: Random crash occurs. iPad 2 (7.0) |  |  | A
2014-09-02 | 67707 | Once: Crash occurs after removing Kwan's armor and weapon. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Move Lightbringer near to the locked Stone Door. 3. Unlock the locked door. 4. During the fight tap on Kwan character and remove Kwan's armor and weapon from inventory tab. 5. Finish the fight and move ahead. Actual Result: Crash occurs. |  |  | A
2014-09-03 | 67913 | The message 'Can't save in Combat' overlaps with Options menu. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Progress and enter in combat. 2. Open Settings menu > Save. 3. Select any slot. Actual Result: The message 'Can't save in Combat' overlaps with Options menu. Expected Result: The message Can't save in Combat' should not overlap with the options menu. Tested on build: v 0.09 Repro rate: 5/5 |  |  | C
2014-09-03 | 67916 | The game fails to display Sell confirmation message while selling the item to merchant. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Access Map > Fast Travel. 3. Select Deep Barrows location. 4. Move and interact with merchant. 5. Sell any item to him. Actual Result: The game fails to display Sell confirmation message while selling the item to merchant. Expected Result: The game should display sell confirmation message while selling the item to merchant. Tested on build: v 0.09 Repro rate: 5/5 |  |  | C
2014-09-03 | 67934 | The player is not able access Pull down menu on 'Fusion Interactive' screen. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Try to access Pull down menu when 'Fusion Interactive' screen appears. Actual Result: The player is not able access Pull down menu on 'Fusion Interactive' screen. Expected Result: The player should be able to access Pull down menu on 'Fusion Interactive' screen. Tested on build: v 0.09 Repro rate: 5/5 |  |  | B
2014-09-03 | 67917 | The Cost of Map is displayed as (minus) -20 coins In the Inventory. | Tested on Build: v 0.09 | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Select Inventory > Select Maximize inventory option > Tap on Map. Actual Result: The Cost of Map is displayed as (minus) -20 coins. Expected Result: Appropriate cost should be displayed for Map. Repro rate: 5/5 |  |  | C
2014-09-03 | 67952 | Screen orientation feature is not implemented on splash and loading screen. |  | 1. Launch Ember RPG. 2. Move iPad upside down till loading screen is completed. Actual Result: Screen orientation feature is not implemented. Expected Result: Screen orientation feature should be implemented on splash and loading screen. | iPad 2 (7.0) |  | C
2014-09-03 | 67953 | In Game screen is displayed for few seconds before the loading screen after quit and relaunch. |  | 1. Launch Ember RPG. 2. Move Lightbringer near to the locked Stone Door. 3. Minimize the game using home button. 4. Full Quit. 5. Relaunch Ember RPG Actual Result: In Game screen is displayed for few seconds. Expected Result: Loading screen should always be displayed while launching the game after full quit. | iPad 2 (7.0) |  | B
2014-09-03 | 67955 | Sword disappears after placing it in Character's inventory tab. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. (Eg. Sword) 3. Equip Time clubber. 4. Move near the locked door. 5. Immediately Open Character's inventory tab and inventory menu. 6. Drag Sword in the character's inventory tab. (Refer to the attachment) Actual Result: Sword disappears. Expected Result: Only one weapon should be placed in the Character's Inventory tab. | iPad 2 (7.0) |  | B
2014-09-03 | 67957 | Leather armor image is not highlighted properly. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. (Eg. Sword) 3. Equip Time clubber. 4. Move near the locked door. 5. Kill Geral and thief and collect items. Actual Result: Leather armor image is not highlighted properly. Expected Result: Leather armor image should be highlighted properly. | iPad 2 (7.0) |  | C
2014-09-03 | 67958 | Potion of health animation is not displayed properly. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. (Eg. Sword) 3. Equip Time clubber. 4. Move near the locked door. 5. Kill Geral and thief and collect items. Actual Result: Potion of health animation is not displayed properly. Expected Result: Potion of health animation should be displayed properly. | iPad 2 (7.0) |  | C
2014-09-03 | 67960 | Screen orientation feature fails to work properly after flipping the device upside down during fight. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. (Eg. Sword) 3. Equip Time clubber. 4. Move near the locked door. 5. During fight flip iPad upside down. Actual Result: Screen orientation feature fails to work properly. Expected Result: Screen orientation feature should work properly. | iPad 2 (7.0) |  | B
2014-09-04 |  | The player is able to interact with Kwan even when the game is paused. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Pause the game. 4. Move the navigation pointer on Kwan. Actual Result: The player is able to interact with Kwan even when the game is paused. Expected Result: The player should be able to interact with Kwan when the game is paused. Repro rate: 5/5 |  | 68181 | B
2014-09-04 |  | The game displays Lightbringer in battle mode even after jumping to another location on the map. |  | 1. Launch Ember RPG. 2. Progress and enter in combat. 2. Access map and select any location. Actual Result: The game displays Lightbringer in battle mode even after jumping to another location on the map. Expected Result: The game should not display Lightbringer in battle mode after jumping to another location on the map. Tested on build: v 0.09 Repro rate: 5/5 |  | 68182 | B
2014-09-04 |  | The player is able to Fast Travel on his current location. |  | 1. Launch Ember RPG. 2. Progress and enter in combat. 2. Access map and choose same location where currently player is located. Actual Result: The player is able to Fast Travel on his current location. Expected Result: The player should not be able to Fast Travel on his current location. Tested on build: v 0.09 Repro rate: 5/5 |  | 68183 | C
2014-09-04 |  | The game displays location name Cemetery after entering in Deep Barrows from Fast Travel. |  | 1. Launch Ember RPG. 2. Access map and select location Deep Barrows. Actual Result: The game displays location name Cemetery after entering in Deep Barrows from Fast Travel. Expected Result: The game should display Deep Barrows as a location name after entering in Deep Barrows. Tested on build: v 0.09 Repro rate: 5/5 |  | 68194 | C
2014-09-04 | 68224 | Skull icon is not properly displayed properly under Inventory menu. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Kill Thief and Geral. 4. Kill Thief and wolf 5. Move towards left side (50022, 49569) Open Crypt and collect items Actual Result: Skull image is too small. Expected Result: Skull image should be displayed properly. | iPad 2 (7.0) |  | C
2014-09-04 | 68230 | Coins and topaz icon is not visible properly. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Kill Thief and Geral. 4. Kill Thief and wolf 5. Collect items. Actual Result: Coins and topaz icon is too small. Expected Result: Coins and topaz icon should be displayed properly. | iPad 2 (7.0) |  | C
2014-09-04 | 68228 | Items collected in the inventory menu collides with each other. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Kill Thief and Geral. 4. Collect items . 5. Drag them and place it together. Actual Result: items collides with each other. Expected Result: items should be placed separately. | iPad 2 (7.0) |  | C
2014-09-04 | 68227 | Enemy body should disappear after collecting items from the dead. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Kill Thief and Geral. 4. Collect items 5. Move out of the screen and come back. Actual Result: Enemy body remains after collecting all the items. Expected Result: Enemy body should disappear after collecting all the items | iPad 2 (7.0) |  | B
2014-09-04 | 68226 | Once: Crash occurs during the first battle with the enemies in Deep Barrows. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Unlock door and start battle. Actual Result: Crash occurs. | iPad 2 (7.0) |  | A
2014-09-04 | 68225 | Game freezes and crash occurs after using Five finger gesture feature during combat under Deep Barrows. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Kill enemies and enter through the portal from stairs up to Stairs down. 4. Kill Riven. 5. Move to position 499997, 49543. 6. During combat using five finger gesture minimize game and re-open. (Refer to the attachment) Actual Result: Crash occurs. | iPad 2 (7.0) |  | A
2014-09-05 | 68467 | Glitch is been observed while moving on stairs in Upper level under Deep Barrows. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Kill enemies and enter through the door to Upper level in Deep Barrows. 4. Walk on the stairs. (Position 50015, 49554) (Refer to the attachment) Actual Result: Glitch is observed. Expected Result: Game should be free from glitches. | iPad 2 (7.0) |  | C
2014-09-05 | 68459 | Crash occurs after finishing the combat with Johan after exiting from Deep Barrow. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Tap on Barrow End Teleportation. 4. Exit Deep Barrows. 5. Complete the conversation with Kwan. 6. Provoke Johan and finish the combat. Actual Result: Crash occurs | iPad 2 (7.0) |  | A
2014-09-05 | 68461 | Zero Damage and zero Average Damage is shown by weapons when the player tries to buy a weapon at the Merchant Shop outside the “Deep Barrows”. |  | 1. Launch Ember RPG game. 2. Play till Lightbringer and Kwan get out of “Deep Barrows”. 3. Outside Deep Barrows talk to the Merchant. 4. Open Inventory Slot and check weapons and stats. Actual Result: Weapons show zero weapon damage and zero Average Weapon Damage. Expected Result: Weapon stats should be accurately. | iPad 2 (7.0) |  | B
2014-09-05 | 68466 | Glitch is observed for split second after moving from Upper level to lower level in Deep Barrows |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Kill enemies and enter through the door to Upper level. 4. Again move to lower level. Actual Result: Glitch is observed. Expected Result: Game should be free from glitches. | iPad 2 (7.0) |  | C
2014-09-05 | 68437 | The game displays "0 Coins" at right bottom corner for all the windows under the Inventory menu. |  | Example: 1. Launch Ember RPG. 2. Select Inventory option from the HUD. 3. Notice the "0 Coins" icon at the right bottom corner of the Armor window. Actual Result: "0 Coins" icon is displayed at right bottom corner of the Armor window. Expected Result: "0 Coins" icon should not be displayed at right bottom corner of the Armor window. Tested on build: v 0.09 Note: This issues is observed for Armor, weapons, Ring, Potion, Misc. and Key window under the Inventory menu. | iPadMini (7.0.4) |  | C
2014-09-05 |  | Game displays cost as '0 coins' for the 2 gold received after defeating any enemy. |  | Example: 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Proceed towards the enemy and Kill enemies. 4. Select Inventory > maximize Inventory view. 5. Click on the dead enemies. 6. Notice the cost displayed for the Gold coins received. Actual Result: Game displays cost as '0 coins' for the 2 gold. Expected Result: Game should not display cost for the Gold. Tested on build: v 0.09 | iPadMini (7.0.4) |  | C
2014-09-08 | 68941 | Crash occurs on the entrance after moving from lower level to Upper level in Deep Barrows |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Kill enemies and enter through the door to Upper level in Deep Barrows. Actual Result: Crash occurs. | iPadMini (7.0.4) |  | A
2014-09-05 | 68945 | Global: Pause menu is invoked during battle while using potions. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Kill enemies and collect items 4. Move right (50021, 49564) in lower level of Deep Barrows. 5. During combat with wolf n thief tap on Inventory menu to eat potion. Actual Result: Pause menu is invoked during combat. Expected Result: While eating potions ' Pause menu' should be disabled during on going combat. | iPadMini (7.0.4) |  | B
2014-09-05 | 68945 | The Game fails to show the Other Quest Locations on the Map. |  | 1. Launch Ember RPG. 2. Play till you get Other Quests. 3. Open Map and check Other quest Location pointer on the Map. Actual Result: The Other Quests Locations are not shown on the Map in the game. Expected Result: The Other Quest Location should be shown on the Map in the Game. | iPadMini (7.0.4) |  | B
2014-09-08 | 68957 | Characters climb above first cave door. |  | 1. Launch Ember RPG. 2. Move towards the first cave door. 3. Move left to the first cave door. 4. Tap above the first cave door. Actual Result: Characters climb above first cave door. Expected Result: Character should not be able to climb above first cave door. Tested on build: v 0.09 Repro rate: 5/5 | iPadMini (7.0.4) |  | C
2014-09-08 | 68959 | The game accepts the input provided by the player when the game is Paused and performs the action when the game is resumed. |  | 1. Launch Ember RPG. 2. Pause the game > Tap anywhere. 3. Resume the game. Actual Result: The game accepts the input provided by the player and performs the action when the game is resumed. Expected Result: The game should not accept the input about the players movement when the game is paused. Tested on build: v 0.09 Repro rate: 5/5 | iPadMini (7.0.4) |  | B
2014-09-09 | 69176 | The game displays re spawn option even if the character is alive after using Hide helmet. |  | 1. Launch the game. 2. Use ‘Barrow End Teleportation’ located near Kwan. 3. Proceed towards right corner near first crypt. (49941, 49484) 4. Collect ‘Hide Helmet’. 5. Enter in any battle. 6. Tap on ‘Hide Helmet' icon as soon as player’s character dies. Actual Result: The game displays re spawn option even if the character is alive after using Hide helmet. Expected Result: The game should not display re spawn option when character is alive. Tested on build: v 0.09 |  |  | B
2014-09-09 | 69177 | The game displays @ instead of Apostrophe (‘) in “Journey through the Sea of Ghost I by Darfire” book. |  | 1. Launch the game. 2. Use ‘Barrow End Teleportation’ located near Kwan. 3. Enter in cave door. 4. Progress towards near Journey through the Sea of Ghost I by Darfire” book. (coordinate 49923,49628) 5. Open the book. Actual Result: The game displays @ instead of Apostrophe (‘) in “Journey through the Sea of Ghost I by Darfire” book. Expected Result: The game should display Apostrophe (‘) instead of @ in “Journey through the Sea of Ghost I by Darfire” book. Tested on build: v 0.09 |  |  | C
2014-09-09 | 69178 | The game displays 'Captain @' word outside page 1 of “Journey through the Sea of Ghost I by Darfire” diary. |  | 1. Launch the game. 2. Use ‘Barrow End Teleportation’ located near Kwan. 3. Enter in cave door. 4. Progress towards near Journey through the Sea of Ghost I by Darfire” diary. (coordinate 49923,49628) 5. Open diary. 6. Observe the first page. Actual Result: The game displays 'Captain @' word outside page 1 of “Journey through the Sea of Ghost I by Darfire” diary. Expected Result: The game should display 'Captain @' within the page 1 of diary. Tested on build: v 0.09 |  |  | C
2014-09-09 | 69180 | Lightbringer fails to collect Basket and/or Health Potion when tapped on Basket and/or Health Potion at coordinate (49895, 49544) in the “Deep Barrows”. |  | 1. Launch Ember RPG. 2. Fast travel to “Deep Barrows”. 3. Go to coordinate (49895, 49544) in Deep Barrows. 4. Tap on the Basket and /or Health Potion. Actual Result: Lightbringer is unable to collect Health potion and/or Basket. Expected Result: Lightbringer should be able to collect Basket and Health Potion. Tested on build: v 0.09 |  |  | B
2014-09-10 | 69380 | Audio is missing for Kwan's dialog after completing “Escape from the Barrows” quest near Cemetery cave door. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Access map and travel to Deep Barrows using Fast Travel option. 4. Move near the stairs. Actual result: Audio is missing for Kwan's dialog when he interacts with Lightbringer . Expected result: The game should play audio for Kwan's dialog when he interacts with Lightbringer. Tested on build: v 0.09 |  |  | C
2014-09-10 | 69382 | The game crashes when player double taps on the book of “Darkwood Teleportation” near the cave door of Cemetery area. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Access map and travel to Deep Barrows using Fast Travel option. 4. Move near the stairs and double tap on the book of “Darkwood Teleportation”. Actual result: The game crashes when player double taps on the book of “Darkwood Teleportation” near the cave door of Cemetery area. Tested on build: v 0.09 |  |  | A
2014-09-10 | 69383 | Audio is missing for Kwan’s dialog “Our journey to Darkwood is of most importance. I urge you to deal with Johan’s request later.” after completing “Escape from the Barrows” near Cemetery cave door. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Access map and travel to Deep Barrows using Fast Travel option. 4. Move near the stairs. 5. Finish conversation with Kwan. 6. When Johan's conversation starts select first option each time. Actual result: Audio is missing for Kwan’s dialog “Our journey to Darkwood is of most importance. I urge you to deal with Johan’s request later.” after completing “Escape from the Barrows” near Cemetery cave door. Expected result: The game should play audio for Kwan's dialog. Tested on build: v 0.09 | 69383 |  | C
2014-09-10 |  | Player is not able to enter upper level of Deep Barrows through the entrance after entering into Cemetery using Barrow End Teleportation. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Tap on Barrow End Teleportation. 4. Move towards to entrance to reach upper level of Deep Barrows Actual Result: Player is not able to enter upper level of Deep Barrows. Expected Result: Player must have access to enter upper level of Deep Barrows |  | iPad 2 (7.0) | A
2014-09-11 | 69592 | The game fails to display Location Last Played date and time on save slot 1 while saving the game. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Save the game on slot 1. 4. Access Save slots again. Observe: Slot 1. Actual result: The game fails to display Location Last Played date and time on save slot 1 while saving the game. Expected result: The game should display Location Last Played date and time on save slot 1 while saving the game. Tested on build: v 0.0953 |  |  | C
2014-09-11 | 69594 | The game does not update the image on save and load slot after overwriting the save slot. |  | For Example 1. Launch Ember RPG. 2. Rescue Kwan. 3. Save the game on slot 3. 4. Access Map and jump to Radiance. 5. Overwrite the save on Slot 3. Observe the image on Slot. Actual result: The game does not update the image on save and load slot after overwriting the save. Expected result: The game updates the image on save slot after overwriting the save slot. Tested on build: v 0.0953 Note: The game updates the image after quitting and relaunching the game. |  |  | C
2014-09-11 | 69595 | Crafting window is empty under the Quest menu. |  | 1. Launch Ember RPG. 2. Tap on the Quest icon. 3. Tap on Crafting Option. Actual Result: Crafting window is empty. Expected Result: craft able items should be displayed in the crafting window. Tested on build: v 0.0953 |  |  | C
2014-09-11 | 69597 | Quit Option is not displayed under Settings Menu. |  | 1. Launch Ember RPG. 2. Tap on Settings under Main Menu. Actual Result: Quit option is missing. Expected Result: Quit option should be displayed. | iPad 2 (7.0) |  | B
2014-09-11 | 69598 | Bear Pelt image is displayed too large as it goes out of the boundry line under inventory menu. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Collect all items after rescuing Kwan. 4. Tap on the Inventory menu > Miscellaneous. Actual Result: Bear Pelt image is too large. Expected Result: Bear Pelt image should be displayed correctly. | iPad 2 (7.0) |  | C
2014-09-11 | 69599 | SFX is missing while switching Weapons and Armor under the inventory menu. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Collect all items after rescuing Kwan. 4. Kill enemies in lower level of Deep Barrows. 5. Collect items. 6. Tap on Inventory > Weapons and switch weapons. Actual Result: SFX is missing while switching the inventory items. Expected Result: The game should play SFX while switching the inventory items. | iPad 2 (7.0) |  | C
2014-09-11 | 69613 | “Lightbringer” spawns in the “Deep Barrows” when clicked on the stairs in the “Cemetery” near the coordinate (49939, 49488). |  | 1. Launch Ember RPG. 2. Fast travel to “Deep Barrows”. 3. Go to the coordinate (49939, 49488) in the “Cemetery”. 4. Click on the Stairs nearby. Actual Result: “Lightbringer” spawns directly in “Deep Barrows”. Expected Result: “Lightbringer” should pass through stairs instead of spawning directly in “Deep Barrows”. | iPad 2 (7.0) |  | C
2014-09-11 | 69616 | Dead body of Lightbringer character move in 360 degree and kwan character remains idle during the combat if the player tap on the map beside Lightbringer's aura. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan 3. Kill enemies (Geral and Theif) 4. Move towards right, get killed by enemies. 5. Tap beside Lightbringer's aura. Actual Result: Dead body of Lightbringer character move in 360 degree. Expected Result: Dead body of Lightbringer character should not move in 360 degree. | iPad 2 (7.0) |  | B
2014-09-11 | 69600 | SFX is missing while pausing the game. |  | 1. Launch Ember RPG. 2. Tap on Settings and listen to the SFX. Actual Result: SFX is missing while Pausing the game. Expected Result: The game should play SFX while Pausing the game. | iPad 2 (7.0) |  | C
2014-09-11 | 69601 | Background Music fails to stop when the player invokes the pause menu. |  | 1. Launch Ember RPG. 2. Tap on Settings and pause the game. Listen to the SFX. Actual Result: Music fails to stop in background. Expected Result: Background Music should stop after pausing the game. | iPad 2 (7.0) |  | B
2014-09-12 | 69840 | User is able to use single Wine item multiple time from the Inventory. | Actual Result: User is able to use single Wine item multiple time. Expected Result: Wine item should disappear from the Inventory after using it. Tested on build: v 0.0954 | 1. Launch Ember RPG. 2. Converse with the Kwan. 3. Go near the Campfire. 4. Collect the Wine. 5. Open Lightbringer inventory. 6. Select Consumable option. 7. Use Wine item multiple times | iPad Mini (7.0.4) |  | C | To Log
2014-09-12 | 69841 | Audio is missing for Kwan's dialog when Lightbringer rescues him. | 1. Launch Ember RPG. 2. Interact with Kwan. Actual result: Audio is missing for Kwan's dialog when Lightbringer rescues him. Expected result: The game should play audio for Kwan's dialog when he interacts with Lightbringer. Tested on build: v 0.0954 | 69841 | iPad Mini (7.0.4) |  | C | To Log
2014-09-12 | 69844 | Audio is missing for Stephan's dialog when Lightbringer rescues him. | 1. Launch Ember RPG. 2. Move and enter in first cave door. 3. Interact with Stephan. Actual Result: Audio is missing for Stephan's dialog when Lightbringer rescues him. Expected Result: The game should play audio for Stephan's dialog when he interacts with Lightbringer. Tested on build: v 0.0954 | 69844 | iPad Mini (7.0.4) |  | C | To Log
2014-09-12 | 69845 | The game drops frame rate heavily while battling with Giant Spider. | 1. Launch Ember RPG. 2. Move and enter in first cave door. 3. Interact with Stephan. 4. Move right side of Stephan and enter in battle with Giant Spider. 5. Observe the frame rate. Actual Result: The game drops frame rate heavily while battling with Giant Spider. Expected Result: The game runs smoothly without dropping framerate. Tested on build: v 0.0954 |  | iPad Mini (7.0.4) |  | B | To Log
2014-09-12 | 69875 | Main Menu button accept input on the Map screen. |  | 1. Launch Ember RPG. 2. Tap on Map > When Map screen is displayed tap on the black screen below 'X'. Actual Result: Main Menu button accept input on the Map screen. Expected Result: Main Menu button should not accept input on the Map screen. | iPad 2 (7.0) |  | B
2014-09-12 | 69866 | Crash occurs while opening the first locked stone door after rescuing kwan. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Tap on the locked stone door to open. Actual Result: Crash occurs. | iPad 2 (7.0) |  | A
2014-09-12 | 69878 | Game accept other input when paused after opening any window while collecting items . |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Move Near the locked door. 4. Tap on Skeleton > Open window > Paused function is invoked. 5. Tap on other items and collect. Actual Result: Game accept other input when paused. Expected Result: Game should not accept other input when paused. | iPad 2 (7.0) |  | B
2014-09-12 | 69877 | “Lightbringer” fails to use the “Potion of Minor Health” after double tapping on it from the “Inventory” when its maximized. |  | 1. Launch Ember RPG. 2. Start new game. 3. Rescue “Kwan”. 4. Kill two “Thief” and “Geral”. 5. Collect the items from two “Thief” and “Geral”. 6. Open “Consumable” tab in the “Inventory” in Detail view. 7. Double tap on the “Potion of the Minor Health”. Actual Result: “Lightbringer” fails to use the “Potion of Minor Health” when double tap. Expected Result: 'Potion of Minor Health' should be used when Double tap. | iPad 2 (7.0) |  | C
2014-09-15 | 70294 | Lightbringer and Kwan is able to kill NPC of lower level when moved to Upper level under Deep Barrows. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Provoke the enemies and without killing them proceed to the entrance of the upper level of Deep Barrows. Actual Result: Kwan is able to kill NPC of lower level in Deep Barrows. Expected Result: Kwan should not kill NPC of lower level in Deep Barrows | iPad 2 (7.0) |  | B
2014-09-15 | 70296 | Storage capacity is not displayed for the Inventory menu. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Collect all the items in lower level of Deep Barrows before Opening second stone door. Actual Result: Storage capacity is not displayed. Expected Result: Storage capacity should be displayed as it help the player to carry important stuff. | iPad 2 (7.0) |  | C
2014-09-15 | 70297 | Cheese thumbnail and image is not displayed while collecting it from the Barrel in Deep Barrows. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Use Barrow End Teleportation. 4. Complete the conversation with Johan. 5. Move around and collect items from Barrel. Actual Result: Cheese thumbnail and image is not displayed Expected Result: Cheese thumbnail and image should be displayed. | iPad 2 (7.0) |  | C
2014-09-15 | 70299 | Inventory items are not interchangeable after keeping it on the Blue slot displayed under Menu. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Collect items. 4. Drag items from the inventory menu and keep it on the blue slots under Main Menu. 5. Close Inventory menu and try to Change the position. Actual Result: Inventory items are not interchangeable. Expected Result: Player should be able to change the item slot after dragging it on and moving it to another. | iPad 2 (7.0) |  | C
2014-09-15 | 70298 | Unlock hint must be given after tapping on the Chest (locked) found in lower level of Deep Barrows. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Open first locked stone door. 4. Move ahead and tap on the Chest (locked). Actual Result: Unlock hint is not displayed after tapping on the locked Chest. Expected Result: Unlock hint should be displayed after tapping on the locked Chest. | iPad 2 (7.0) |  | B
2014-09-15 | 70300 | Player is unable to collect Red Apple displayed near the thief in Deep Barrows. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Use Barrow End Teleportation. 4. Complete the conversation with Johan. 5. Move around and try to collect the Red apple displayed near the thief. Actual Result: Player is unable to collect Red Apple. Expected Result: Player should be able to collect Red Apple. | iPad 2 (7.0) |  | C
2014-09-15 | 70304 | The game fails to display current location of character on Local map. |  | 1. Launch Ember RPG. 2. Access Local map. Actual Result: The game fails to display current location of character on Local map. Expected Result: The game displays current location of character on local map. Tested on build: v 0.0954 | iPad Mini (7.0.4) |  | C
2014-09-16 | 70529 | Deer Hide image is displayed too large as it goes out of the boundry line under inventory menu. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Kill enemies and move near Altar of the Blue. 4. Collect Deer Hide > Tap on the Inventory menu > Miscellaneous. Actual Result: Deer Hide image is too large. Expected Result: Deer Hide image should be displayed correctly. | iPad 2 (7.0) |  | C
2014-09-16 | 70581 | Kwan remains idle in battle when Lightbringer is battling with enemies using Bow. |  | 1. Launch Ember RPG. 2. Rescue Kwan and choose Bow weapon. 3. Enter in first cave door. 4. Move towards left side. 5. Hit the thief from distance with Bow. Actual Result: Kwan remains idle in battle when Lightbringer is battling with enemies using Bow. Expected Result: Kwan should interact in battle as soon as Lightbringer starts battling with enemies. Tested on build: v 0.0954 |  |  | B
2014-09-17 | 70795 | Back button is not displayed on Save Slot and load game window. |  | Example: 1. Launch Ember RPG. 2. Tap on Settings > Save > Save Game. Actual Result: Back button is missing. Expected Result: Back button should be displayed. |  |  | C
2014-09-17 | 70801 | Corpse window overlaps with the collected items name |  | For Example 1. Launch Ember RPG. 2. Rescue Kwan. 3. Enter in first battle and defeat enemies. 4. Tap on a Dead Body and Collect Ragged pinnacle Hide Armor. 5. Observe that 'Ragged' text appears behind the Corpse window. Actual Result: Corpse window overlaps with the collected items name Expected Result: Collected items name appears without any overlapping. Tested on build: v 0.0954 Note: This issue also occurs on PC
2014-09-18 | 71073 | The game displays Fishing Rod out of inventory menu. |  | For Example 1. Launch Ember RPG. 2. Rescue Kwan. 3. Explore Deep barrows and collect some items. 5. Move in Cemetery area. 6. Access Inventory and Drag Live Fish on Lightbringer. Actual Result: The game crashes after dragging an item on Lightbringer. Tested on build: v 0.0954 iPad Air (7.1.2) |  |  | C
2014-09-18 | 71084 | The user receives 'The Ale Run: The Five best Ale Houses in Domus!' Part 1 and 2 multiple times after interacting with 'Horace the Drunk' multiple times. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Progress and start quest 06 'Knowledge is Our Greatest Weapon'. 4. Move near Darius the teacher. 5. Interact with Horace the Drunk. 6. Repeat step no 5. Actual Result: The user receives 'The Ale Run: The Five best Ale Houses in Domus!' Part 1 and 2 multiple times after interacting with 'Horace the Drunk' multiple times. Expected Result: The user should receive The Ale Run: The Five best Ale Houses in Domus!' Part 1 and 2 only once. Tested on build: v 0.0954 iPad Air (7.1.2) |  |  | B
2014-09-18 | 71089 | Kwan stucks near the door after returning back from Cemetery to Deep Barrows. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Progress and enter into Cemetery area. 4. Return back to Deep Barrows. Actual Result: Kwan stucks near the door after returning back from Cemetery to Deep Barrows. Expected Result: Kwan should move with Lightbringer after returning back from Cemetery to Deep Barrows. Tested on build: v 0.0954 iPad Air (7.1.2) |  |  | B
2014-09-18 | 71073 | The game crashes after dragging an item on Lightbringer. |  | For Example 1. Launch Ember RPG. 2. Rescue Kwan. 3. Explore Deep barrows and collect some items. 5. Move in Cemetery area. 6. Access Inventory and Drag Live Fish on Lightbringer. Actual Result: The game crashes after dragging an item on Lightbringer. Tested on build: v 0.0954 iPad Air (7.1.2) |  |  | A
2014-09-18 | 71105 | Crash occurs after resuming the device from sleep while moving from lower level to upper level. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. kill all enemies and while moving from lower level to upper level put the device in sleep mode and resume it quickly. Actual Result: Crash occurs | iPad 2 (7.0) |  | A
2014-09-19 | 71375 | Player is able to consume Red potion even after the Lightbringer is dead. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Collect all the items and proceed. 4. During Fight get killed from thief's. 5. Once your dead, open inventory menu and tap of the Red potion. Actual Result: Red potion can be consumed even if the player's character is already dead. Expected Result: Potion should be consumed only if the player is alive or the player's party member. | iPad 2 (7.0) |  | B
2014-09-19 | 71376 | iPad 2 (7.0): A major framerate drop is observed during the fight with thief in lower level of Deep Barrows. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Collect all the items and proceed. 4. During Fight get killed from thief's. Actual Result: framerate drop is observed during the on going combat of Kwan and thief. Expected Result: The game should function smoothly. | iPad 2 (7.0) |  | B
2014-09-19 | 71377 | Game Over and Respawn option fails to appear immediately after player's character and party member are dead. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Collect all the items and proceed. 4. During combat with thief get killed along with party member (Kwan). Actual Result: Game Over and Respawn option fails to appear immediately . Expected Result: Game Over and Respawn option should appear immediately after characters are dead. | iPad 2 (7.0) |  | B
2014-09-19 | 71372 | The game fails to display current objective information on Map. |  | For Example 1. Launch Ember RPG. 2. Rescue Kwan. 3. Progress and complete quest no 16 'The Salty Keg'. 4. Open Quest menu. 5. Observe current objective 'Speak to Monte' 6. Access the Map. 7. Notice that the game only displays location of the current objective and information about the same is missing. Actual Result: Objective information is not displayed on the Map. Expected result: The game displays current objective information on the Map. Tested on build: v 0.0954 iPad Air (7.1.2) Note: It will help user if the information about the next objective is displayed on the Map. |  |  | C
2014-09-19 | 71373 | The game fails to display current location icon on the map when user accesses the maps four to five times continuously. |  | For Example 1. Launch Ember RPG. 2. Rescue Kwan. 3. Progress and complete quest no 16 'The Salty Keg'. 4. Access the map continuously four to five times. 5. Notice that current location icon disappears from the Map. Actual Result: The game fails to display current location icon on the map when user accesses the maps four to five times continuously. Expected Result: The game displays current location on the Map every time when the user accesses the Map. Tested on build: v 0.0954 iPad Air (7.1.2) |  |  | B
2014-09-19 | 71374 | Kwan and Corra remains on the ground floor when Lightbringer interacts with Argyle on first floor while completing quest no 16 'The Salty Keg'. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Progress and start quest 16 'The Salty Keg'. 4. Move in a building where Argyle is available on first floor. Actual Result: Kwan and Corra remains on the ground floor when Lightbringer interacts with Argyle on first floor while completing quest no 16 'The Salty Keg'. Expected Result: Kwan and Corra moves on first floor when Lightbringer moves. Tested on build: v 0.0954 iPad Air (7.1.2) |  |  | C
2014-09-22 | 71909 | Lightbringer is able to collect items even after getting killed. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Collect all items after rescuing Kwan. 4. Kill enemies in lower level of Deep Barrows. 5. Make Lightbringer health low. (Do not consume potion) 6. Proceed to Upper level of Deep Barrows. 7. After entering into Upper level move towards east where two thief and dead skeleton are seen. 8. Get killed from thief and tap on dead skeleton. Actual Result: Lightbringer is able to collect items Expected Result: Lightbringer should not collect items when dead. | iPad Air (7.1.2) This issue is also observed on PC. |  | B
2014-09-22 | 71910 | Kwan is seen on full HP/SP after getting killed from A.I. |  | 1. Launch Ember RPG. 2. Complete the conversation with Kwan. 3. Collect all items after rescuing Kwan. 4. Kill enemies in lower level of Deep Barrows. 5. Move to upper level kill enemies > Check Kwan experience bar. 6. Get Kwan killed before level up. 7. Kill enemies Actual Result: Kwan is seen of full HP/SP when dead. Expected Result: Kwan HP/SP should be full when respawned. | iPad Air (7.1.2) This issue is also observed on PC. |  | B
2014-09-22 | 71911 | Corpse window overlaps with Couldn’t take all items text prompt when the inventory is full. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Kill enemies and collect all items 4. Try to collect items from Corpse window when inventory is full. Actual Result: Couldn’t take all items text prompt is overlapped Expected Result: Couldn't take all items text should be displayed without overlapping. Tested on build: v 0.0954 Note: This issue also occurs on PC | iPad Air (7.1.2) This issue is also observed on PC. |  | C
2014-09-22 | 71912 | Kwan receives damage and get killed from resurrected skeleton even when the skeleton is not seen on the screen. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Kill enemies and collect all items. 4. Move to Upper level > tap on Crypt. 5. When Skeleton hits Kwan. 6. Run towards bottom side. Actual Result: Kwan receives damage even when the skeleton is not seen on the screen. Expected Result: Skeleton should be displayed in the screen when engaged with Kwan. | iPad Air (7.1.2) This issue is also observed on PC. |  | B
2014-09-22 | 71913 | SFX is missing for scrolling arrow while scrolling the list in inventory. |  | 1. Launch Ember RPG. 2. Rescue Kwan. 3. Progress and collect few items. 4. Open Inventory > Misc. 5. Tap on the Scrolling arrow. Actual Result: SFX is missing for scrolling arrow while scrolling the list in inventory. Expected Result: The game plays SFX while scrolling the list in inventory. Tested on build: v 0.0954 iPad Air (7.1.2) |  |  | C | To Log
2015-11-16 | 151613 | iPad Air 2 (9.0): Crash occurs after resuming the game from the sleep mode for the second time. |  | 1. Install and launch the game. 2. Rescue Corren 3. Progress a game till Bog of Souls. 4. Quit game > Relaunch the game. 5. Tap on Continue, lock and unlock the screen immediately. 6. Black is observed for infinite period of time. ( Home button fails to work) 7. Again keep the device in sleep mode and resume it quickly. Actual Result: Crash occurs after resuming the device from sleep mode. Expected Result: User should able to progress the game without crash.
2015-11-16 | 151618 | Game progression is very difficult while completing the quest 'Bastille Day' in Normal difficulty. |  | 1. Install and launch the game. 2. Rescue Corren. 3. Progress the game and start Bastille Day Quest. Actual Result: Game progression is very difficult while completing Bastille Day Quest. Expected Result: Difficulty level should be nerved
2015-11-17 | 151754 | Crash occurs on Continue button when user switch between the apps. |  | 1. Install and launch the game. 2. Rescue Corren 3. Progress a game till Bog of Souls. 4. Quit game. 5. Open Settings > Minimize Settings. 6. Relaunch the game. 7. Tap on Continue, immediately switch to settings and again switch back to the game. Actual Result: Crash occurs on switching between the apps. Expected Result: User should able to progress the game without crash.
2015-11-17 | 151753 | Ember Goddess texture is missing throughout the game. |  | 1. Install and launch the game. 2. Rescue Corren 3. Progress a game till Final Battle. Notice: Ember Goddess. Actual Result: Texture is missing. Expected Result: Ember Goddess texture should be displayed while completing the Final Battle.
2015-11-17 | 151752 | Icon is missing over the head of King Harfast in Ember Mines. |  | 1. Install and launch the game. 2. Rescue Corren 3. Progress a game Ember and proceed to King Harfast. Notice the icon over the head of Kind Harfast. Actual Result: icon is missing over the head of King Harfast Expected Result: icon should be displayed over the head of King Harfast
2015-11-17 | 151755 | The Local map for White Ember Portal seems very glitchy. |  | 1. Install and launch the game. 2. Rescue Corren 3. Progress a game till Quest the Goddess Bond. 4. Enter White Ember Portal and notice the Local Map. Actual Result: White Ember Portal local map is seen very glitch. Expected Result: A proper path should be displayed in White Ember Portal Local map to reach the quest location.
2015-11-17 | 151767 | Progression block is seen after defeating the Ember Goddess. |  | 1. Install and launch the game. 2. Rescue Corren 3. Progress a game till Final Battle. 4. Defeat Ember Goddess. 5. Tap on Quest and check the objectives. Actual Result: Progression block after defeating the Ember Goddess. Expected Result: The Quest should be displayed in Complete tab after defeating the Ember Goddess.